## KPI
Headline KPIs per reporting week. Edit values weekly. Add a column for a new week (header WkNN).
Metric | Wk64 | Wk65 | Wk66
status | on-track | on-track | on-track
statusText | Overall: On Track | Overall: On Track | Overall: On Track
statusDotColor | #2e7d32 | #2e7d32 | #2e7d32
sum_kpi_overall | 56.9% | 59.3% | 61.5%
sum_kpi_overall_vs | Vs. Planned 55.4% (+1.5% Ahead) | Vs. Planned 57.5% (+1.8% Ahead) | Vs. Planned 59.6% (+1.9% Ahead)
sum_kpi_spi | 1.04 | 1.05 | 1.06
sum_kpi_hse | 1,210K | 1,250K | 1,310K
sum_kpi_risks | 1 | 0 | 0
sum_kpi_action | 2 | 0 | 0
sum_kpi_int | 9 | 8 | 6
sum_kpi_ncr | 3 | 2 | 1
sum_kpi_punch | 48 | 45 | 38

## Phase
Workfront % per week. P = Planned, A = Actual. Numbers only (0-100). Row order is fixed.
Workfront | P64 | A64 | P65 | A65 | P66 | A66
Detailed Engineering | 100 | 100 | 100 | 100 | 100 | 100
Procurement | 83.5 | 85.5 | 86 | 88.5 | 88.5 | 91
Fabrication Yards | 85 | 87 | 88 | 90 | 91 | 93
Transportation & Load-out | 40 | 42 | 43 | 45 | 46 | 48
Site Construction | 23 | 25 | 25.7 | 27.8 | 28 | 30.5
System Commissioning | 0 | 0 | 0.5 | 1 | 2 | 3

## Sections
Detailed per-tab fields (section.field). Keep the exact text format shown (e.g. "388 / 450 T", "99.0%"). Do not rename Key.
Key | Wk64 | Wk65 | Wk66
engineering.prog | 100% | 100% | 100%
engineering.prog_vs | Planned: 100% (KD18 met 01-Jun-27) | Planned: 100% (KD18 met 01-Jun-27) | Planned: 100% (KD18 met 01-Jun-27)
engineering.docs | 2,560 | 2,560 | 2,560
engineering.docs_vs | 2,560 of 2,560 (Code 1 & 2) | 2,560 of 2,560 (Code 1 & 2) | 2,560 of 2,560 (Code 1 & 2)
engineering.hazop | 100% | 100% | 100%
engineering.hazop_vs | All actions closed at AFC | All actions closed at AFC | All actions closed at AFC
engineering.tq | 0 | 0 | 0
procurement.prog | 85.5% | 88.5% | 91.0%
procurement.prog_vs | Planned: 83.5% (+2.0% Ahead) | Planned: 86.0% (+2.5% Ahead) | Planned: 88.5% (+2.5% Ahead)
procurement.po | 16 / 16 | 16 / 16 | 16 / 16
procurement.delay | 5 / 16 | 6 / 16 | 8 / 16
procurement.overdue | 0 | 0 | 0
fabrication.prog | 87.0% | 90.0% | 93.0%
fabrication.prog_vs | Planned: 85.0% (+2.0% Ahead) | Planned: 88.0% (+2.0% Ahead) | Planned: 91.0% (+2.0% Ahead)
fabrication.welds | 32,600 | 34,200 | 35,300
fabrication.ndt | 99.0% | 99.2% | 99.3%
fabrication.ton | 388 / 450 T | 405 / 450 T | 420 / 450 T
logistics.prog | 42.0% | 45.0% | 48.0%
logistics.mws | 3 / 4 | 4 / 4 | 4 / 4
logistics.weight | 1,562 T | 1,562 T | 1,562 T
logistics.damage | 0 | 0 | 0
site.prog | 25.0% | 27.8% | 30.5%
site.prog_vs | Planned: 23.0% (+2.0% Ahead) | Planned: 25.7% (+2.1% Ahead) | Planned: 28.0% (+2.5% Ahead)
site.ptw | 22 | 24 | 28
site.simops | SIMOPS Restrict | SIMOPS Restrict | SIMOPS Restrict
site.tie | 10 / 45 | 12 / 45 | 19 / 45
commissioning.prog | 0.0% | 1.0% | 3.0%
commissioning.sys | 12 | 12 | 12
commissioning.sheet | 0 / 480 | 15 / 480 | 42 / 480
commissioning.punch | 48 | 45 | 38
hse.lti | 0 | 0 | 0
hse.obs | 780 | 820 | 890
hse.weld | 1.7% | 1.4% | 1.2%
hse.ncr | 3 | 2 | 1

## Variance
Schedule-variance chart points per week (13 values, negative = behind).
Week | V1 | V2 | V3 | V4 | V5 | V6 | V7 | V8 | V9 | V10 | V11 | V12 | V13
64 | 0 | 0 | -2 | -3 | -1 | -4 | -2 | 0 | 0 | -1 | -2 | 0 | 0
65 | 0 | 0 | -3 | -4 | -5 | -4 | -3 | -2 | 0 | 0 | -2 | -3 | 0
66 | 0 | 0 | 0 | -2 | -5 | -3 | -3 | -2 | 0 | 0 | -2 | -3 | 0

## Milestones
Key Dates. Status = completed ¦ in-progress ¦ not-started. Update Forecast/Status as the project progresses.
Name | Baseline | Forecast | Status
KD 01 - Effective Date (ED) | 01-Jul-2026 | 01-Jul-2026 | completed
KD 02 - KOM & Key Personnel Mobilized | 08-Jul-2026 | 08-Jul-2026 | completed
KD 07 - Detailed Work Plan Approved | 30-Jul-2026 | 30-Jul-2026 | completed
KD 10-13 - PO for Major Packages Placed | 31-Aug-2026 | 31-Aug-2026 | completed
KD 16 - Detailed Engineering 50% IFC | 15-Dec-2026 | 15-Dec-2026 | completed
KD 17 - TCC Earthworks & Foundations | 13-Feb-2027 | 13-Feb-2027 | completed
KD 18 - Detailed Engineering 100% IFC | 01-Jun-2027 | 01-Jun-2027 | completed
KD 20 - TCC Readiness Certificate | 30-Jun-2027 | 30-Jun-2027 | completed
KD 21 - Slug Catcher Delivered to SITE | 01-Dec-2027 | 01-Dec-2027 | not-started
KD 22 - TEG Unit Delivered to SITE | 29-Jan-2028 | 29-Jan-2028 | not-started
KD 23 - Metering Unit Delivered to SITE | 29-Jan-2028 | 29-Jan-2028 | not-started
KD 24 - Functional Ready for Commissioning | 05-May-2028 | 05-May-2028 | not-started
KD 27 - Provisional Acceptance Certificate | 03-Jan-2029 | 03-Jan-2029 | not-started

## Engineering
Engineering discipline progress heatmap. Actual/Target are numbers (0-100).
Name | Actual | Target | Status
Process | 100 | 100 | on-track
Piping & Layout | 100 | 100 | on-track
Mechanical | 100 | 100 | on-track
Civil/Struct | 100 | 100 | on-track
Electrical | 100 | 100 | on-track
Instrument | 100 | 100 | on-track
Safety/HSE | 100 | 100 | on-track
ICSS | 100 | 100 | on-track
Telecom | 100 | 100 | on-track
Comm. Eng. | 100 | 100 | on-track

## Procurement
Long-lead packages. Prog is a number (0-100). PO/FAT/Site are dates (dd-Mmm-yyyy).
Name | PO | FAT | Site | Prog
Pig Receiver (AA-8133) | 30-Sep-2026 | 01-Sep-2027 | 30-Nov-2027 | 100
Slug Catcher (V-8133) | 31-Aug-2026 | 01-Sep-2027 | 30-Nov-2027 | 100
TEG Package (C-8160 / A-8160) | 31-Aug-2026 | 31-Oct-2027 | 29-Jan-2028 | 94
Mercury Removal Unit (A-8170) | 01-Sep-2026 | 01-Nov-2027 | 30-Jan-2028 | 93
ICSS Cabinets | 31-Aug-2026 | 02-Aug-2027 | 16-Sep-2027 | 100
Gas Fiscal Metering (M-8101) | 31-Aug-2026 | 31-Oct-2027 | 29-Jan-2028 | 94
HIPPS Package | 31-Aug-2026 | 02-Aug-2027 | 16-Sep-2027 | 100
HV Switchboard | 31-Aug-2026 | 13-Jun-2027 | 28-Jul-2027 | 100
Electrical Room | 31-Aug-2026 | 30-Oct-2027 | 28-Jan-2028 | 96
Instrument Room | 31-Aug-2026 | 30-Oct-2027 | 28-Jan-2028 | 96
HP Separator (V-8151) | 30-Nov-2026 | 26-Sep-2027 | 25-Dec-2027 | 100
Condensate Pump A/B (P-8151) | 31-Dec-2026 | 29-Jul-2027 | 27-Oct-2027 | 100
Water Pump A/B (P-8152) | 31-Dec-2026 | 29-Jul-2027 | 27-Oct-2027 | 100
Condensate Metering (M-8102) | 31-Aug-2026 | 01-Oct-2027 | 30-Dec-2027 | 99
Water Metering Skid (M-8103) | 31-Aug-2026 | 01-Oct-2027 | 30-Dec-2027 | 99
Flow Control Station (FCV-332) | 31-Aug-2026 | 22-Oct-2027 | 28-Jan-2028 | 78

## SCurve
Overall S-Curve baseline (Plan Rev.00), monthly Jun-26 to May-29. Reference data — rarely changes. Numbers are cumulative % except the two Monthly* increment columns.
Month | MonthlyPhysical | MonthlyMilestone | OverallCum | MilestoneLabel | OverallPlan | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | WP9 | WP10
Jun-26 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jul-26 | 0.356 | 8 | 8.36 | Mobilization of KEY PERSONNEL & Contract KOM | 0.59 | 3.06 | 0 | 5.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aug-26 | 1.917 | 5 | 15.27 | Submission CCM, Local Communities, Management Plan, Security Plan for APPROVAL | 3.79 | 6.23 | 0 | 10.82 | 8.75 | 0 | 0 | 0 | 0 | 0 | 0
Sep-26 | 0.955 | 0 | 16.23 |  | 5.38 | 9.3 | 5.43 | 15.15 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0
Oct-26 | 1.08 | 0 | 17.31 |  | 7.18 | 12.46 | 11.15 | 19.63 | 12.79 | 0 | 0 | 0 | 0 | 0 | 0
Nov-26 | 2.201 | 0 | 19.51 |  | 10.85 | 15.53 | 16.69 | 23.97 | 21.43 | 0 | 0 | 0 | 0 | 0 | 0
Dec-26 | 1.604 | 1 | 22.11 | DE 50% IFC Return Code 1&2 | 13.52 | 18.69 | 22.42 | 28.45 | 26.58 | 0 | 0.78 | 0 | 0 | 0 | 0
Jan-27 | 1.282 | 0 | 23.4 |  | 15.66 | 21.86 | 28.14 | 32.93 | 29.42 | 1.11 | 2.52 | 0.09 | 0 | 0 | 0
Feb-27 | 1.304 | 1 | 25.7 | Completion of all earthworks and foundations for TCC | 17.83 | 24.72 | 32.24 | 37.37 | 29.78 | 8.89 | 4.08 | 1.3 | 0 | 0 | 0
Mar-27 | 3.504 | 0 | 29.2 |  | 23.67 | 27.89 | 35.59 | 45.41 | 42.44 | 14.67 | 5.81 | 2.63 | 0 | 0 | 0
Apr-27 | 2.12 | 0 | 31.32 |  | 27.21 | 30.95 | 38.83 | 53.45 | 47.03 | 21.95 | 7.49 | 3.93 | 0 | 0 | 0
May-27 | 2.253 | 0 | 33.58 |  | 30.96 | 34.12 | 42.18 | 61.75 | 48.21 | 41.19 | 9.38 | 5.27 | 0 | 0 | 0
Jun-27 | 2.145 | 1 | 36.72 | DE 100% IFC Return Code 1&2 | 34.54 | 37.18 | 45.43 | 69.79 | 49.08 | 59.8 | 12.2 | 6.57 | 0 | 0 | 0
Jul-27 | 5.743 | 3 | 45.46 | TCC READINESS CERTIFICATE | 44.11 | 40.35 | 47.98 | 75.58 | 63.27 | 79.03 | 18.28 | 15.16 | 0 | 0 | 0
Aug-27 | 4.281 | 0 | 49.75 |  | 51.24 | 43.51 | 50.51 | 81.07 | 72.94 | 86.94 | 24.46 | 24 | 0 | 0 | 0
Sep-27 | 3.023 | 0 | 52.77 |  | 56.28 | 46.58 | 52.96 | 82.93 | 77.04 | 93.43 | 30.45 | 32.56 | 0 | 0 | 0
Oct-27 | 3.758 | 0 | 56.53 |  | 62.54 | 49.74 | 55.49 | 84.68 | 84.88 | 100 | 36.63 | 41.4 | 0 | 0 | 0
Nov-27 | 3.077 | 0 | 59.6 |  | 67.67 | 52.81 | 57.93 | 86.37 | 91.47 | 100 | 42.61 | 49.95 | 0 | 0 | 0
Dec-27 | 2.386 | 3 | 64.99 | Slug Catcher delivered to SITE | 71.65 | 55.98 | 60.46 | 88.11 | 93.88 | 100 | 48.8 | 58.79 | 0 | 0 | 0
Jan-28 | 2.347 | 1.5 | 68.84 | TEG, Metering Unit delivered to SITE | 75.56 | 59.14 | 62.99 | 89.86 | 96.06 | 100 | 54.98 | 67.63 | 0 | 0 | 0
Feb-28 | 2.063 | 0 | 70.9 |  | 79 | 62.1 | 65.36 | 91.49 | 97.38 | 100 | 60.77 | 75.9 | 0 | 0 | 0
Mar-28 | 2.42 | 0 | 73.32 |  | 83.03 | 65.27 | 67.89 | 93.06 | 100 | 100 | 66.95 | 84.74 | 0 | 0 | 0
Apr-28 | 1.915 | 0 | 75.24 |  | 86.23 | 68.34 | 70.33 | 93.67 | 100 | 100 | 72.94 | 93.29 | 3.19 | 0 | 0
May-28 | 1.899 | 3.5 | 80.64 | READY FOR COMMISSIONING CERTIFICATE | 89.39 | 71.5 | 72.86 | 94.3 | 100 | 100 | 77.51 | 100 | 23 | 0 | 0
Jun-28 | 0.743 | 0 | 81.38 |  | 90.63 | 74.57 | 75.31 | 94.91 | 100 | 100 | 81.56 | 100 | 42.17 | 0 | 0
Jul-28 | 0.752 | 3 | 85.13 | ACHIEVEMENT OF COMMISSIONING CERTIFICATES | 91.88 | 77.73 | 77.84 | 95.55 | 100 | 100 | 85.74 | 100 | 52.14 | 26.88 | 0
Aug-28 | 0.948 | 0 | 86.08 |  | 93.46 | 80.9 | 80.37 | 96.18 | 100 | 100 | 89.92 | 100 | 59.76 | 60.22 | 33.33
Sep-28 | 0.917 | 0 | 86.99 |  | 94.99 | 83.96 | 82.81 | 96.79 | 100 | 100 | 93.97 | 100 | 67.14 | 92.47 | 65.59
Oct-28 | 0.793 | 0 | 87.79 |  | 96.31 | 87.13 | 85.34 | 97.43 | 100 | 100 | 98.16 | 100 | 74.75 | 100 | 98.92
Nov-28 | 0.575 | 5 | 93.36 | PROVISIONAL ACCEPTANCE CERTIFICATE | 97.27 | 90.19 | 87.79 | 98.04 | 100 | 100 | 99.07 | 100 | 86.33 | 100 | 100
Dec-28 | 0.589 | 0 | 93.95 |  | 98.25 | 93.36 | 90.32 | 98.67 | 100 | 100 | 99.89 | 100 | 98.44 | 100 | 100
Jan-29 | 0.506 | 5 | 99.46 | Completed of Start-up CERTIFICATE | 99.1 | 96.53 | 94.79 | 99.31 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Feb-29 | 0.446 | 0 | 99.9 |  | 99.84 | 99.39 | 99.08 | 99.88 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Mar-29 | 0.096 | 0 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Apr-29 | 0 | 0 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
May-29 | 0 | 0 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100

## WPInfo
Work Package names + S-curve weighting (Σ=100).
WP | Name | Weight
WP1 | Management & Project Control | 10
WP2 | Temporary Construction Camp | 10
WP3 | Engineering | 5
WP4 | Procurement & Supply | 30
WP5 | Pre-Fabrication & Mech. Completion | 10
WP6 | Transport, Storage & Load-out | 2
WP7 | Construction & MC at SITE | 28
WP8 | Commissioning & Start-up | 3
WP9 | Operation & Maintenance | 1
WP10 | Final Documentation & Data | 1